## Sheet1
Section | Details
Project Name | Automted Independent Validation System
Application Name | ParaBank
Objective | To check whether registration, account creation, transfer funds and account overview are working correctly
Scope | Registration, open account, transfer funds, account overview, negative testing
Out of scope | Heavy performance testing, production deployment
Testing type | Functional testing, UI testing, Negative testing, Hybrid testing
Test approach | Manual validation + Playwright automation
Tools used | Playwright, typescript, VS code, Github Copilot(MCP)
Test environment | Windows
Browser used | Chromium, webkit, firefox
Test Data | JSON test data
Deliverables | Automation script, test cases, RTM, Defect report
Entry criteria | Application should be accessible
Exit criteria | Major scenario executed
Risks | Internal server errors may stop execution
Defect tracking | Maintained in defectReport.xlsx
Status | Completed